## Summaries
Title | B. Instance Tabular Summary
Entity Type | Instance
Report Type | Tabular
View | All Instances -
Created by | Carlo
Created at | 23-Jul-2020 02:10 (UTC)

## Data
ID | TestSet: Frequency | TestSet: Waste Type | Test: ID | Test: Name | Test: Run Status | Linked Issues | Test: Linked Issues
1:1 |  |  | 1 | Check Environment Configuration | PASSED | 1 | [[1 "Differences in Sandbox Configuration V Spreadsheets"]]
2:1 |  |  | 3 | Add a PO Chain | FAILED |  | []
2:2 |  |  | 4 | Create ORDER | PASSED |  | []
2:3 |  |  | 5 | Upload Documents | FAILED |  | []
3:1 |  |  | 3 | Add a PO Chain | FAILED |  | []
3:2 |  |  | 4 | Create ORDER | PASSED |  | []
3:3 |  |  | 5 | Upload Documents | FAILED |  | []
7:1 | Weekly | Grease Trap | 3 | Add a PO Chain | FAILED |  | []
7:2 | Weekly | Grease Trap | 4 | Create ORDER | PASSED |  | []
7:3 | Weekly | Grease Trap | 5 | Upload Documents | FAILED |  | []
8:1 | Weekly | Paper | 3 | Add a PO Chain | FAILED |  | []
8:2 | Weekly | Paper | 4 | Create ORDER | PASSED |  | []
8:3 | Weekly | Paper | 5 | Upload Documents | FAILED |  | []
9:1 | Weekly | GWD | 3 | Add a PO Chain | FAILED |  | []
9:2 | Weekly | GWD | 4 | Create ORDER | PASSED |  | []
9:3 | Weekly | GWD | 5 | Upload Documents | FAILED |  | []
10:1 | Weekly | SEWR | 3 | Add a PO Chain | FAILED |  | []
10:2 | Weekly | SEWR | 4 | Create ORDER | PASSED |  | []
10:3 | Weekly | SEWR | 5 | Upload Documents | FAILED |  | []
11:1 | On Call | Grease Trap | 3 | Add a PO Chain | FAILED |  | []
11:2 | On Call | Grease Trap | 4 | Create ORDER | PASSED |  | []
11:3 | On Call | Grease Trap | 5 | Upload Documents | FAILED |  | []
12:1 | On Call | Paper | 3 | Add a PO Chain | FAILED |  | []
12:2 | On Call | Paper | 4 | Create ORDER | PASSED |  | []
12:3 | On Call | Paper | 5 | Upload Documents | FAILED |  | []
13:1 | On Call | GWD | 3 | Add a PO Chain | FAILED |  | []
13:2 | On Call | GWD | 4 | Create ORDER | PASSED |  | []
13:3 | On Call | GWD | 5 | Upload Documents | FAILED |  | []
14:1 | On Call | SEWR | 3 | Add a PO Chain | FAILED |  | []
14:2 | On Call | SEWR | 4 | Create ORDER | PASSED |  | []
14:3 | On Call | SEWR | 5 | Upload Documents | FAILED |  | []
16:1 |  |  | 1 | Check Environment Configuration | PASSED |  | [[1 "Differences in Sandbox Configuration V Spreadsheets"]]
17:1 | On Call | GWD | 8 | Add PO Chain | NO RUN |  | []
17:2 | On Call | GWD | 9 | Create ORDER | NO RUN |  | []
17:3 | On Call | GWD | 10 | Upload Documents | NO RUN |  | []
17:4 | On Call | GWD | 11 | Add an on call job to a service | NO RUN |  | []
17:5 | On Call | GWD | 12 | Lodging/Assigning a Communication | NO RUN |  | []
17:6 | On Call | GWD | 13 | respond to an assigned Communication | NO RUN |  | []
17:7 | On Call | GWD | 14 | View Billing Vs Service Site | NO RUN |  | []
17:8 | On Call | GWD | 15 | Amending a Service Frequency - days | NO RUN |  | []
17:9 | On Call | GWD | 16 | Amending a Service Frequency - Collection Interval | NO RUN |  | []
17:10 | On Call | GWD | 17 | Cancelling an Active Account | NO RUN |  | []
17:11 | On Call | GWD | 18 | Adding an on-call Service Note to a specific service | NO RUN |  | []
17:12 | On Call | GWD | 19 | Book HIAB movement | NO RUN |  | []
17:13 | On Call | GWD | 20 | View Service History by Service | NO RUN |  | []
17:14 | On Call | GWD | 21 | View Service History by Site | NO RUN |  | []
17:15 | On Call | GWD | 22 | View rates history | NO RUN |  | []
17:16 | On Call | GWD | 23 | Placing an account on Suspend | NO RUN |  | []
17:17 | On Call | GWD | 24 | Cancel a Routed Job (one-off) | NO RUN |  | []
17:18 | On Call | GWD | 25 | Changing a service date (on-off) | NO RUN |  | []
17:19 | On Call | GWD | 26 | Suspending an order for holiday Closures | NO RUN |  | []
17:20 | On Call | GWD | 27 | Suspending Services with fixed advanced pricing over holiday closures | NO RUN |  | []
17:21 | On Call | GWD | 28 | Locating a closed/Suspended account | NO RUN |  | []
18:1 | Weekly | GWD | 8 | Add PO Chain | NO RUN |  | []
18:2 | Weekly | GWD | 9 | Create ORDER | NO RUN |  | []
18:3 | Weekly | GWD | 10 | Upload Documents | NO RUN |  | []
18:4 | Weekly | GWD | 11 | Add an on call job to a service | NO RUN |  | []
18:5 | Weekly | GWD | 12 | Lodging/Assigning a Communication | NO RUN |  | []
18:6 | Weekly | GWD | 13 | respond to an assigned Communication | NO RUN |  | []
18:7 | Weekly | GWD | 14 | View Billing Vs Service Site | NO RUN |  | []
18:8 | Weekly | GWD | 15 | Amending a Service Frequency - days | NO RUN |  | []
18:9 | Weekly | GWD | 16 | Amending a Service Frequency - Collection Interval | NO RUN |  | []
18:10 | Weekly | GWD | 17 | Cancelling an Active Account | NO RUN |  | []
18:11 | Weekly | GWD | 18 | Adding an on-call Service Note to a specific service | NO RUN |  | []
18:12 | Weekly | GWD | 19 | Book HIAB movement | NO RUN |  | []
18:13 | Weekly | GWD | 20 | View Service History by Service | NO RUN |  | []
18:14 | Weekly | GWD | 21 | View Service History by Site | NO RUN |  | []
18:15 | Weekly | GWD | 22 | View rates history | NO RUN |  | []
18:16 | Weekly | GWD | 23 | Placing an account on Suspend | NO RUN |  | []
18:17 | Weekly | GWD | 24 | Cancel a Routed Job (one-off) | NO RUN |  | []
18:18 | Weekly | GWD | 25 | Changing a service date (on-off) | NO RUN |  | []
18:19 | Weekly | GWD | 26 | Suspending an order for holiday Closures | NO RUN |  | []
18:20 | Weekly | GWD | 27 | Suspending Services with fixed advanced pricing over holiday closures | NO RUN |  | []
18:21 | Weekly | GWD | 28 | Locating a closed/Suspended account | NO RUN |  | []
19:1 |  |  | 39 | Configuration - Set up a Driver | NO RUN |  | []
19:2 |  |  | 40 | Configuration - Set up a Vehicle | NO RUN |  | []
19:3 |  |  | 41 | Configuration - Set up a Trailer Type | NO RUN |  | []
19:4 |  |  | 42 | Configuration - Set up a Container Type | NO RUN |  | []
19:5 |  |  | 43 | Configuration - Set up an Owner Driver | NO RUN |  | []
19:6 |  |  | 44 | Configuration - Set up a Subcontractor | NO RUN |  | []
19:7 |  |  | 45 | Configuration - Set up a Disposal Location | NO RUN |  | []
19:8 |  |  | 46 | Configuration - Set up a Default Action | NO RUN |  | []
19:9 |  |  | 47 | Container Maintenance | NO RUN |  | []
19:10 |  |  | 48 | Create a new Run | NO RUN |  | []
19:11 |  |  | 49 | Allocate scheduled jobs to a Run | NO RUN |  | []
19:12 |  |  | 50 | Allocate a new job to a Run while on the road | NO RUN |  | []
19:13 |  |  | 51 | Manually Mark a Job as complete | NO RUN |  | []
19:14 |  |  | 52 | Manually Mark a Job as incomplete (futile) | NO RUN |  | []
19:15 |  |  | 54 | Allocate a Driver to a Run | NO RUN |  | []
19:16 |  |  | 55 | Allocate a Truck to the run | NO RUN |  | []
19:17 |  |  | 57 | Check Status | NO RUN |  | []
20:1 |  |  | 29 | Login | NO RUN |  | []
20:2 |  |  | 30 | Logout | NO RUN |  | []
20:3 |  |  | 31 | Receive a new Job while on Run | NO RUN |  | []
20:4 |  |  | 32 | View Job Details | NO RUN |  | []
20:5 |  |  | 33 | Mark a Job as contaminated | NO RUN |  | []
20:6 |  |  | 34 | Mark a Job as futile | NO RUN |  | []
20:7 |  |  | 35 | Mark a job as Complete | NO RUN |  | []
20:8 |  |  | 36 | Disposal | NO RUN |  | []
20:9 |  |  | 37 | Go on a break | NO RUN |  | []
20:10 |  |  | 38 | Complete a Route | NO RUN |  | []
20:11 |  |  | 53 | Finish a Run | NO RUN |  | []
21:1 | Weekly | GWD | 60 | Form 44 - When send to vehicle is unticked form is not sent to vehicle | BLOCKED |  | [[111 "Form 44 - Not available on WPF"]]
21:2 | Weekly | GWD | 61 | Form 44 - When send to vehicle is ticked form is sent to vehicle | BLOCKED |  | [[111 "Form 44 - Not available on WPF"]]
21:3 | Weekly | GWD | 62 | Form 44 - Valid Until is Optional | FAILED |  | [[111 "Form 44 - Not available on WPF"]]
21:4 | Weekly | GWD | 63 | Form 44 - Valid From is Mandatory | BLOCKED |  | [[111 "Form 44 - Not available on WPF"]]
21:5 | Weekly | GWD | 64 | Form 44 - An expired Form 44 is not sent to vehicle | NO RUN |  | []
21:6 | Weekly | GWD | 65 | Form 44 - An expired Form 44 can be updated | NO RUN |  | []
21:7 | Weekly | GWD | 66 | Form 44 - Multiple Valid Form 44 can be present | NO RUN |  | []
21:8 | Weekly | GWD | 67 | Form 44 - Correct Pages are viewable on the OBC | NO RUN |  | []
21:9 | Weekly | GWD | 68 | Form 44 - An warning message appears when assigning a job with an invalid Form 44 | NO RUN |  | []
21:10 | Weekly | GWD | 59 | Form 44 can be uploaded to WEB | PASSED |  | []
21:11 | Weekly | GWD | 69 | Form 44 - When send to vehicle is unticked form is not sent to vehicle | NO RUN |  | []
21:12 | Weekly | GWD | 70 | Form 44 - When send to vehicle is ticked form is sent to vehicle | NO RUN |  | []
21:13 | Weekly | GWD | 71 | Form 44 - Valid Until is optional | NO RUN |  | []
21:14 | Weekly | GWD | 72 | Form 44 - Valid From is Mandatory | PASSED |  | []
21:15 | Weekly | GWD | 73 | Form 44 - An expired Form 44 is not sent to vehicle | NO RUN |  | []
21:16 | Weekly | GWD | 74 | Form 44 - An expired Form 44 can be updated | NO RUN |  | []
21:17 | Weekly | GWD | 75 | Form 44 - Only 1 Valid Form 44 can be present | NO RUN |  | []
21:18 | Weekly | GWD | 76 | Form 44 - Correct Pages are viewable on the OBC | PASSED |  | []
21:19 | Weekly | GWD | 77 | Form 44 - An warning message appears when assigning a job with an invalid Form 44 | NO RUN |  | []
22:1 | Weekly | Paper | 60 | Form 44 - When send to vehicle is unticked form is not sent to vehicle | BLOCKED | 111 | [[111 "Form 44 - Not available on WPF"]]
22:2 | Weekly | Paper | 61 | Form 44 - When send to vehicle is ticked form is sent to vehicle | BLOCKED | 111 | [[111 "Form 44 - Not available on WPF"]]
22:3 | Weekly | Paper | 62 | Form 44 - Valid Until is Optional | FAILED | 111 | [[111 "Form 44 - Not available on WPF"]]
22:4 | Weekly | Paper | 63 | Form 44 - Valid From is Mandatory | BLOCKED | 111 | [[111 "Form 44 - Not available on WPF"]]
22:5 | Weekly | Paper | 64 | Form 44 - An expired Form 44 is not sent to vehicle | NO RUN |  | []
22:6 | Weekly | Paper | 65 | Form 44 - An expired Form 44 can be updated | NO RUN |  | []
22:7 | Weekly | Paper | 66 | Form 44 - Multiple Valid Form 44 can be present | NO RUN |  | []
22:8 | Weekly | Paper | 67 | Form 44 - Correct Pages are viewable on the OBC | NO RUN |  | []
22:9 | Weekly | Paper | 68 | Form 44 - An warning message appears when assigning a job with an invalid Form 44 | NO RUN |  | []
22:10 | Weekly | Paper | 59 | Form 44 can be uploaded to WEB | PASSED |  | []
22:11 | Weekly | Paper | 69 | Form 44 - When send to vehicle is unticked form is not sent to vehicle | NO RUN |  | []
22:12 | Weekly | Paper | 70 | Form 44 - When send to vehicle is ticked form is sent to vehicle | NO RUN |  | []
22:13 | Weekly | Paper | 71 | Form 44 - Valid Until is optional | NO RUN |  | []
22:14 | Weekly | Paper | 72 | Form 44 - Valid From is Mandatory | PASSED |  | []
22:15 | Weekly | Paper | 73 | Form 44 - An expired Form 44 is not sent to vehicle | NO RUN |  | []
22:16 | Weekly | Paper | 74 | Form 44 - An expired Form 44 can be updated | NO RUN |  | []
22:17 | Weekly | Paper | 75 | Form 44 - Only 1 Valid Form 44 can be present | NO RUN |  | []
22:18 | Weekly | Paper | 76 | Form 44 - Correct Pages are viewable on the OBC | PASSED |  | []
22:19 | Weekly | Paper | 77 | Form 44 - An warning message appears when assigning a job with an invalid Form 44 | NO RUN |  | []
22:20 | Weekly | Paper | 58 | Form 44 can be uploaded to WPF | NO RUN |  | []