## Summaries
|  | Title | C. Issue Tabular Summary Report
|  | Entity Type | Issue
|  | Report Type | Tabular
|  | View | All Issues -
|  | Created by | Carlo
|  | Created at | 23-Jul-2020 02:11 (UTC)
Status | Count
closed | 37
fixed | 13
assigned | 49
opened | 1
ready to test | 4
new | 5
<NO VALUE> | 0
Assigned To | Count
Jackie | 6
Carlo | 16
Syed | 5
Alex | 5
Karen | 6
HenryF | 1
Chris | 8
Pramod | 55
Ashok | 1
Conrad | 4
<NO VALUE> | 2
Priority | Count
3-normal | 22
2-high | 77
1-showstopper | 7
4-low | 3
<NO VALUE> | 0

## Data
ID | Title | Status | Assigned To | Priority | Last Modified | Application | Description | Type
1 | Differences in Sandbox Configuration V Spreadsheets | closed |  | 3-normal | 24-Jun-2020 07:37 | ELEMOS WPF | Differences between v8.3.0.42 in Sandbox | Defect
2 | Config v0.4 - No of Days cannot be zero for On-Call Service Frequency | fixed | Jackie | 2-high | 26-Jun-2020 06:19 | ELEMOS WPF | Cannot load On-Call Service Frequency in ELEMOS. Link to Config v0.4 File. https://teams.microsoft.com/l/file/2D42BAE2-6B59-4265-B12E-310171361B72?tenantId=f4a12867-922d-4b9d-bb85-9ee7898512a0&fileType=xlsm&objectUrl=https%3A%2F%2Fone4u.sharepoint.com%2Fsites%2FProjectPierTeamCollaborationHub%2FShared%20Documents%2F3.%20Data%20Migration%2F05%20Staging%2F01%20Data%20Loads%2FPIER%20Config%20Data%20v0.4.xlsm&baseUrl=https%3A%2F%2Fone4u.sharepoint.com%2Fsites%2FProjectPierTeamCollaborationHub&serviceName=teams&threadId=19:f1dfdd8290764307add2d80b64e3fbff@thread.skype&groupId=c3cdb515-02c8-4099-9dad-4642d2226c19 ServiceFrequency 1 On-Call No of Days: Must be set or mark as Monthly | Defect
3 | Differences between Dev and Test | closed | Carlo | 3-normal | 29-Jun-2020 04:50 | ELEMOS WPF | Comparison done on 23/06/2020 | Defect
5 | Config v0.4 - Field missing in Service Object | fixed | Syed | 2-high | 25-Jun-2020 00:59 | ELEMOS WPF | Line of Business: Required. Service 1 BALING ¦ Transport Line of Business: Required. Service 2 BULK TRANSPORT ¦ Transport Line of Business: Required. Service 3 CRANE TRUCK ¦ Transport Line of Business: Required. Service 4 DATA SECURITY ¦ Transport Line of Business: Required. Service 5 DRAIN CLEANING ¦ Transport Line of Business: Required. Service 6 FRONT END LIFT ¦ Transport Line of Business: Required. Service 7 HIGH PRERSSURE WATER BLASTING ¦ Transport Line of Business: Required. Service 8 HOOKLIFT ¦ Transport Line of Business: Required. Service 9 LIQUID COLLECTION ¦ Transport Line of Business: Required. Service 10 MEDICAL COLLECTION ¦ Transport Line of Business: Required. Service 11 MEDICAL TREATMENT ¦ Transport Line of Business: Required. Service 12 PACKAGED WASTE ¦ Transport Line of Business: Required. Service 13 PANTECH ¦ Transport Line of Business: Required. Service 14 PRODUCT DESTRUCTION ¦ Transport Line of Business: Required. Service 15 REAR END LIFT ¦ Transport Line of Business: Required. Service 16 ROLLOFF ¦ Transport Line of Business: Required. Service 17 ROUTE WEIGHING ¦ Weighbridge Line of Business: Required. Service 18 SKIPS ¦ Transport Line of Business: Required. Service 19 SWEEPER ¦ Transport Line of Business: Required. Service 20 TRANSFER STATION ¦ Administration Line of Business: Required. Service 21 VACUUM COLLECTION ¦ Transport Line of Business: Required. Service 22 MINES ¦ Transport Line of Business: Required. After the upgrade of ELEMOS 8.3, there is a new mandatiry field Line of Business, that needs to be populated which was not available in BDL API. Course of Action: AMCS to include in the BDL API. PIER need to include in Config upload file. Ashok needs to modify the migration program, test and load. | Defect
6 | Config v0.4 - Field missing in Company Object | fixed | Syed | 2-high | 25-Jun-2020 00:59 | ELEMOS WPF | Missing field Leislation Type. Company 1 SITA Australia Pty Ltd ¦ AUD Legislation Type: Must have a value. Company 2 SITA Regional Qld Pty Ltd ¦ AUD Legislation Type: Must have a value. Company 3 Perthwaste Pty Ltd ¦ AUD Legislation Type: Must have a value. Company 4 SUEZ R&R NZ ¦ NZD Legislation Type: Must have a value. After the upgrade of ELEMOS 8.3, there is a new mandatiry field Line of Business, that needs to be populated which was not available in BDL API. Course of Action: AMCS to include in the BDL API. PIER need to include in Config upload file. Ashok needs to modify the migration program, test and load. | Defect
7 | Config v0.4 - Australian RegEx issue | assigned | Alex | 2-high | 25-Jun-2020 01:10 | ELEMOS WPF | Cannot load 1800, 1300 and 13 phone numbers in ELEMOS due to RegEx not setup for these numbers. Phone Numbers are mandatory loaded 18, 13 numbers with "00000000". | Defect
8 | Config v0.4 - Accounting Period 2ecd and Leap Year | fixed | Karen | 2-high | 25-Jun-2020 23:32 | ELEMOS WPF | Checks performed in the PIER Config Data v0.4 expected: The end date for February 2020 should be 29/02/2020 Actual: The end date for February 2020 is 28/02/2020 | Defect
9 | Config v0.4 - Action 4e97 | fixed | Karen | 2-high | 26-Jun-2020 00:18 | ELEMOS WPF | Checks performed against PIER COnfig Data v0.4 Expected: Rebateable bin should be present in action 4e97 Actual: Rebateable binis absent from 4e97 | Defect
10 | Config v0.4 - Default Actions not loaded | fixed | Karen | 2-high | 26-Jun-2020 03:57 | ELEMOS WPF | Removal (R) ¦ Data Security Removal (R) ¦ Pantech | Defect
11 | Config v0.4 - Communication Type 21be | assigned | Carlo | 2-high | 02-Jul-2020 06:42 | ELEMOS WPF | Expected: For each value in the worksheet, the Values input in CommunicationMethodID, CommunicationOutcomeID and CommunicationCLassificationID should be ticked in WPF. Actual: The values are not ticked. | Defect
12 | Config v0.4 - Company 60c0 | fixed | Carlo | 2-high | 30-Jun-2020 03:40 | ELEMOS WPF | Expected: As per the migration spreadsheet, SUEZ R&R NZ should have a Bank Detail ValidationContext of "NZ Format" Actual: SUEZ R&R NZ has a Bank Detail ValidationContext of "AU Format" | Defect
13 | Config v0.4 - Company Outlet 3ead | assigned | Carlo | 2-high | 08-Jul-2020 06:20 | ELEMOS WPF | Issue 1 - Extra space in Geelong Service Centre Expected: "Geelong Service Centre" should only have one space between each words Actual: There are 2 spaces between Geelong and Service Issue 2 - Outlet was not created Expected: "Wesfarmers Curragh Mine should be present" Actual: Wesfarmers is not present Corrected Geelong Removed a space Issue 2 Branch has advised it is Curragh Mine previously? I have removed Wesfarmers due another persons request. Cam you please advise how you are hearing about Wesfarmenrs so I can followup? | Defect
14 | Config v0.4 - Location 23f9 | assigned | HenryF | 2-high | 06-Jul-2020 06:07 | ELEMOS WPF | Expected: Location Latitude and Location Longitude should be populate in WPF Actual: Fields are blank | Training
15 | Containers v0.4 - Records not loaded | fixed | Chris | 2-high | 29-Jun-2020 06:17 | ELEMOS WPF | Expected: 2 Records with description of Bags 2 records with description of Bin Liners Actual: 1 record with description of Bags 1 record with description of Bin Liners | Defect
16 | Unable to Save Customer | closed | Alex | 1-showstopper | 06-Jul-2020 04:08 | ELEMOS WPF | Whilst trying to create a customer, Elemos allowed me to get all the way to the end of the initial creation process before getting an error message which prevents me from saving the customer. | Defect
17 | Masterdata load issue | opened | Karen | 2-high | 02-Jul-2020 00:01 | ELEMOS WPF | Pump out- service Pallets Tick box should be selected for Initiate Weighing Seems to be only when primary action is create job from | Defect
18 | Customer Creation Failure | closed | Pramod | 2-high | 06-Jul-2020 04:56 | ELEMOS Web | Elemos Web UI doesn't allow the creation of a new Customer. Once you click on the 'New Customer' button, the first field you need to complete is the address. I typed in one single digit and received the attached error message. | Config
19 | Default Action -Waste Types Dropdown box not working | assigned | Carlo | 2-high | 14-Jul-2020 01:31 | ELEMOS WPF | Created a Default Action Manually called Removal (R) against 1.Pantech 2.Data Security The drop down box is not allowing me to allocate the Waste Type against the Action Also having an inconsistent experience on the Migrated Default Actions Some have the material drop down box as changeable Some have the material drown down box as locked. | Defect
20 | Company Names not relating to correct outlets | fixed | Karen | 3-normal | 14-Jul-2020 01:29 | ELEMOS WPF | In the test system, if you go to Copmany outlets, some of the outlewts have the worng company name, eg. Brisbane C&D is under Perthwaste, same as Shoalhaven. Might be a migration data error. Both of these are Sita Australia Pty Ltd outlets. | Defect
21 | Currency GBP - has not been removed | closed | Alex | 3-normal | 29-Jun-2020 04:23 | ELEMOS WPF | GBP Still exists under Settings->FInance->Currency | Defect
22 | Mobile Settings to remove Compulsory Settings | closed | Chris | 3-normal | 14-Jul-2020 01:51 | AMCS Mobile | Seeking AMCS to provide detials of settings either in WPF or Mobile to remove Compulsory settings on Tag/Serial number for containers, Cusomter Signature and Driver Signatures. | Defect
23 | Service Agreement Template is set up, but does not get used. | closed | Carlo | 2-high | 29-Jun-2020 06:18 | ELEMOS Web | Expected: Attempting to view an Active Contract using ELEMOS WEB should be possible if an active service agreement template exists. Actual: Error message appears, http failure response 500 No internal Service Agreement Template Set up for Routed Commercial (see screenshot "NO SA - error.png") To recreate: 1. Ensure that a Service Agreement Template exists, by going into Settings, Service Agreement Templates 2. Locate a Customer named "Conrete Structure Pty" 3. In the Active COntracts frame, click on "REL G/W" | Defect
24 | Material Details cannot be input when creating an Order | assigned | Pramod | 1-showstopper | 14-Jul-2020 01:39 | ELEMOS Web | Users can normally input a Material and Material Profile when creating an order using ELEMOS WPF. In ELEMOS WEB however, there are no values in these dropdowns. To Recreate: 1. Locate Concrete Structure Pty LTY using ELEMOS WEB 2. In the Active Work Order section, click on Add 3. Select "REL G/W" in the Service Agreement 4. Click on COntinue 5. Change the Destination to Erskine Park Transfer Station 6. Attempt to input the Material and Material Profile Expected: When creating an order, user should be able to input Material and Material Profile Actual: No values are present from these 2 dropdowns. NOte: A comparison of behaviour between WEB and WPF is attached as a video. | Defect
25 | Cannot edit Customer Details | assigned | Pramod | 3-normal | 16-Jul-2020 02:27 | ELEMOS Web | Users are able to modify customer Name, ABN, etc. using ELEMOS WPF. Attempting to do this using ELEMOS WEB returns an error message. To recreate: 1. Using Elemos WEB, locate customer CONCRETE PTY LT 2. In the Details section, click on Edit Expected: Further Customer details should be presented Actual: Error message appears "Edit not supported for this customer as the business type is not set on the customer record." | Defect
26 | No Status is selectable when creating a new Communication using Web | assigned | Syed | 2-high | 16-Jul-2020 00:23 | ELEMOS Web | To recreate: 1. Locate record: Concrete Structure Pty LTRD 2. In the Communication Details Section, click on Add 3. Select Complaint as Type 4. Select Driver Complaint as Classification 5. Select Telephone as Method 6. Attempt to Input a status Expected: A value should be selectable Actual: No value is available. Communication cannot be saved. | Config
27 | No Outcome or Classification is selectable when creating a new Communication using WPF | assigned | Syed | 2-high | 16-Jul-2020 00:25 | ELEMOS WPF | to recreate using the Thick Client: 1. Locate a customer ACAMPANA 2. In customer Option, click on Open Communications 3. Click on New 4. Attempt to select a value in Classification 5. Attempt to select a value in Outcome Expected: Dropdowns Classification and Outcome should contain a few values | Config
28 | Config v0.4 - CommunicationTypes and CommunicationClassifications | closed | Syed | 2-high | 06-Jul-2020 04:09 | ELEMOS WPF | The Communication Matrix submitted to Syed was not migrated over into 8.3. All Communications are not set up correctly with relevant criteria. | Defect
29 | System.ArgumentException when creating a new Customer | closed | Pramod | 2-high | 06-Jul-2020 04:56 | ELEMOS WPF | to recreate in ELEMOS WPF: 1. Click on the Customer Home Sector 2. Search for a Customer Name starting with "KENSINGTON ST" 3. Click on New Customer Expected: New Customer Wizard should appear Actual: Popup message describing a System.ArgumentException appears (see the screenshot) | Config
30 | Wild Card Search is not working in WebUI | closed | Pramod | 3-normal | 06-Jul-2020 04:08 | ELEMOS Web | When performing a wild card search in WebUI Elemos (%%%) - error message appears. | Enhancement
31 | Area of Origin - Config missing | fixed | Chris | 3-normal | 30-Jun-2020 23:54 | ELEMOS WPF | We need to construct and load Area of Origin in Configuration. This is required for Route Management | Defect
32 | Medical Containers | fixed | Chris | 2-high | 06-Jul-2020 03:56 | ELEMOS WPF | No Bins linked to Medical collection and processing in Container Settings. | Defect
33 | Container Size is not configured correctly. Needs fix up in V0.5 Config | fixed | Chris | 2-high | 23-Jul-2020 01:44 | ELEMOS WPF | Identified that the set up on Config v0.4 for the cotnianer size is not correct. Resulting in the volume calcualitions being grossly inflated. Config v0.5 needs to be modified to reflect the correct sizes. Eg. 660lt needs to be expressed as 0.66 | Defect
34 | Input of new prices - When an error is detected, all input is cancelled | closed | Pramod | 4-low | 06-Jul-2020 04:57 | ELEMOS Web | When entering new prices against an order, error correction exists to ensure that the effective date of the price is never earlier than the effective date of the linked service agreement. However, when this message appears, ELEMOS WEB exits the input of prices, requiring the user to instead, input the prices all over again. Expected: Elemos WPF should instead, display the error message and give the user an opportunity to rectify the error without having to inputer prices all over again. | Enhancement
35 | Activate Customer Health & Safety Tab | closed | Carlo | 2-high | 01-Jul-2020 05:55 | ELEMOS WPF | The Customer Health & Safety Tab needs to be enabled in the Test environment, to allow the upload of Form 44 against the site. | Defect
36 | PO's and PO Chains cannot be created | closed | Jackie | 2-high | 14-Jul-2020 05:31 | ELEMOS Web | When trying to create a PO Chain to later on link the individual PO's, you are required to enter a naming convention and then a start and end date. Regardless of the dates being entered, an error message appears requesting dates to be entered. This same error occurs in Web UI and WPF. | Defect
37 | Attempting to add an order results in an infinite loop | closed | Pramod | 2-high | 01-Jul-2020 06:43 | ELEMOS WPF | To recreate using ELEMOS WPF: 1. locate ACCC1009 2. Click on Service agreements 3. Open the Service Agreement 4. On the bottom right of the Customer Service Agreement Editor, click on OK and Order Wizard 5. Input Order details 6. Click ok Expected: Order should be created against the Service Agreement Actual: Order wizard appears again See video | Issue
38 | Elemos System Config Regex validation - Not accepting Toll free numbers | assigned | Ashok | 2-high | 06-Jul-2020 05:54 | ELEMOS WPF | Elemos regex validation not accepting Toll fee number. Ex - 131335 BDL error - "Description": "Tel No: Must match a valid telephone number format.", Regex validation should pass/accept valid australia numbers. | Issue
39 | AMCS Mobile - Tag & Container is mandatory. Request this is turned off | assigned | Pramod | 2-high | 21-Jul-2020 23:47 | AMCS Mobile | SUEZ does not currently record serial number or tag numbers for contianer deliveries. Request that hte mandatory requirmeent on Mobile be deactivated. | Training
40 | Customer Signature is mandatory | closed | Pramod | 2-high | 14-Jul-2020 01:51 | AMCS Mobile | When delivering a container, the customer signature screen requires a mandatory signature. As per previsou requests, this should not be mandatory. | Issue
41 | Multiple container deliveries and unified workflow | assigned | Pramod | 2-high | 21-Jul-2020 23:36 | AMCS Mobile | When delivering more than one container to a cusomters site, each contianer requires the dirver to enter various data. ? Can the unified workflow be turned off for Contianer Deliveries? ? If not, how can we make the process more seamless to the driver. | Issue
42 | Route Assignments and the New Order Wizard | closed | Pramod | 3-normal | 14-Jul-2020 01:55 | ELEMOS WPF | When creating a new order, there are 2 unexpected values encountered: 1. Day of Week: Unplanned 2. Interval: Adhoc Where do these come from? Do we need them? | Issue
43 | Volume Planning - Container Size & Conversion Factor | assigned | Chris | 2-high | 14-Jul-2020 02:54 | ELEMOS WPF | During our testing, we have identified an issue with the functionality of the new Volume Planning. In the configuration of containers, we enter the Container size for example, 1.5 for a 1.5m3 container or 660 for a 660lt Rearlift container. We have checked the notes supplied on Volume Planning, but it is silent on this topic. From what we can see, the system does not factor or use the Conversion factor from the Unit of Measure, it only takes the unit from the Container size entered. Logically, we thought: - - the container size is entered in the container Type as its actual size, eg. 1.5 for a 1.5m3, or 660 for a 660lt, 240 for a 240lt MGB. - The unit of measurement is set up so that m3 is the Base Unit of Measurement. - Set the Litres UOM with a conversion factor of 1000 (being 1000lt = 1m3) - When the volume planning is calculated, the system looks at the unit of Measure and any conversions to provide the correct volume. From our various testing and changing many of the settings, it appears the coding is hard coded from the Container size. And with all due respect, the user Story is operating this way. However, the business will always refer to a 240lt container as a 240, not a 0.24. | Enhancement
44 | Keyboard persistent - When reviewing Drivers Instructions, the Keyboard appears | assigned | Conrad | 3-normal | 13-Jul-2020 04:05 | AMCS Mobile | From the drivers route, when you tap on the clipboard to review the drivers instructions, the keyboard appears. This was to be rectified from the last release. The system seems to think that feedback is being entered, and the keyboard appears. For a driver, this is not practical. They just want ot read the instruction, and not have to tap extra keys. | Defect
45 | Unified workflow for Routed work - Signature required for all jobs | closed | Pramod | 2-high | 14-Jul-2020 03:01 | AMCS Mobile | Since the upgrade a number of obvious functionalities have vanished. This is for Routed work: 1. When you click on job, perform the list, and then click on the green tick to confirm the job, the screen goes to a signature screen. (In routed work, we do not require cusotmers to sign (so this should be disabled) | Issue
46 | Access Times - Elemos WPF and Mobile not matching | assigned | Pramod | 2-high | 22-Jul-2020 00:48 | AMCS Mobile | The access times being entered in Elemos are not presenting on the mobile device the same. There appears to be a time zone setting imapct. | Issue
47 | Destination not pulling through to the Mobile device | assigned | Pramod | 2-high | 22-Jul-2020 04:04 | AMCS Mobile | The destination is set on the Route template. The route is created and sent to the device. When the user on the device , goes to the "disposal screen", the destination does not pull through. | Issue
48 | Unit of Measure for Disposal needs to be set to Tonnes, not Kilograms | ready to test | Carlo | 2-high | 14-Jul-2020 06:01 | AMCS Mobile | In TEST environment prior to deployment, the units were set at Tonnes. In the version 0.4 config it has been set to Kilograms, which was incorrect. The version 0.5 has been changed to Tonnes and will rake effect in next full data migration. Changing the base unit of measurement is prevented in the UI so that already created transactions will not be corrupted. In the interim Suez have requested AMCS force a change which will corrupt existing data but allow new data to be adhered to veriosn 0.5 data spec. Modifcation Required: 1. Un-Check 'base UOM' for 'KG' record. 2. Check 'base UOM' for 'Tonne' record. 3. Change the 'Conversion factor' for 'KG' record to 1000. 4. Change the 'Conversion factor' for 'Tonne' record to 1. | Config
49 | Debrief Screen - Planned Metres | assigned | Pramod | 2-high | 21-Jul-2020 23:39 | AMCS Mobile | Identidied that the figure coming through on this screen is to 16 decimal points. This jsut needs to eb to 2 decimal points. Also, as a enhancement the actual lifts and actual metres could be presented on this screen. | Enhancement
50 | Order Creation Error | closed | Pramod | 2-high | 06-Jul-2020 04:54 | AMCS Mobile | When getting to the final stage estabishing a work order to deliver a 4m skip contianer (Chris Buldings), the following error appeared: No Suitable Docuemnt Identifier has been configured for this compnay or company outlet" See attachment. | Config
51 | Error message: Entity of type VehicleTrailEntity with id 0... | assigned | Pramod | 4-low | 17-Jul-2020 07:56 | AMCS Mobile | To recreate: 1. Log on to OBC 2. On the top right, click on 3 dots 3. Cick on VIsit History on the popout menu Expected: no messages to appear on the grey bar at the bottom Actual: Message appears "The entity of type VehicleTrailEntity with id 0 in list obq already existed and was overwritten by the SQLiteLocalDataManager". Screenshot attached. | Defect
52 | Create and Schedule Call Out - Radius shows Yards | assigned | Pramod | 3-normal | 06-Jul-2020 06:24 | ELEMOS Web | Web needs to be configured, so that value of the Radius dropdown shows metres, rather than yeards To Recreate: Follow the steps in the video | Issue
53 | Unified workflow for Routed work - Not possible to input number of bins serviced | closed | Pramod | 2-high | 16-Jul-2020 01:20 | AMCS Mobile | Since the upgrade a number of obvious functionalities have vanished. This is for Routed work: 2. When you do put a signature in, the job automatically completes. There is no ability to confirm the number of lifts. In the previous version, a screen came up and allowed you to select the number of lifts. It defaulted to the number in the job. This is required for sites where there are say 4 bins on site, and we only tip 3 of them. | Issue
54 | Unified workflow for Routed work - Timeout Function when job is completed | closed | Chris | 2-high | 03-Jul-2020 06:43 | AMCS Mobile | Since the upgrade a number of obvious functionalities have vanished. This is for Routed work: 3. When the job is completed, the Timeout function has gone. This was a great setting, whihc allowed the driver to pull the job back within 10 seconds of completing the job. | Issue
55 | Form 44 functionality - not passing to jobs and onto device | closed | Pramod | 2-high | 03-Jul-2020 04:52 | AMCS Mobile | A Form 44 is set up in Web UI for th customer. However, when the job is allocated to a route, it does not pass through and ultimately is not coming to the Device. | Issue
56 | System 404 Error when reviewing job - Web UI allows the pointer Finger, but only triggers a 404 Error | assigned | Carlo | 2-high | 20-Jul-2020 06:50 | ELEMOS Web | For a Proskip cusomter "Chris Buildings", we had delivered and removed a 4m Skip continaer. From the cusotmer screen (as per attached) , when you click on the actual job activity - Delivery of 4m Skip, an error occurs. See attached. | Issue
57 | Scheduled Job - Disposal data not coming across to the job | closed | Pramod | 1-showstopper | 21-Jul-2020 07:16 | ELEMOS WPF | When reviewing the job for Chris Buildings, 4m Skip removal, I entered the disposal data equating to 2200kg, and took a photo of a docket. When the job has been completed, no disposal data has come across. We have run another delivery and removal, with the same result. | Issue
58 | Customer Template Error: TEMPLATE NOT FOUND | assigned | Pramod | 2-high | 14-Jul-2020 03:00 | ELEMOS Web | When creating a new Customer through the Web UI, although there is a valid template against the outlet, the system allows you to search and locate a site address, but once you try and save it an error appears saying 'NO TEMPLATE FOUND' | Defect
59 | Keyboard is Persistent - Additional Charges | assigned | Carlo | 2-high | 10-Jul-2020 05:20 | AMCS Mobile | When adding an additional charge (or if the + button is accidentally pressed), the only way to go back to the main screen is to click on Cancel. The keyboard is stuck. This is an issue because on landscape orientation, the Cancel Button is obscured by the keyboard. To recreate on OBC on Landscape orientation: 1. Locate a job 2. Click on the + icon 3. Click on the Search field to start typing 4. Attempt to dismiss the keyboard Expected: Clicking outside the keyboard should dismiss it Actual: It's impossible to dismiss the keyboard | Issue
60 | Material not pulling through on Disposal Screen | assigned | Pramod | 2-high | 22-Jul-2020 04:13 | AMCS Mobile | This is the reverse of Issue #47. For Scheduled work, the destination ias pulling through, but the Material type is not. | Issue
61 | Containers on Site - Not displaying on Scheduled jobs | assigned | Pramod | 2-high | 22-Jul-2020 12:12 | ELEMOS WPF | During set up for Proskips simulation, I replicated Monday 6th July Run. This resulted in forcing deliveries onto Sunday 5th July, which have been completed manually. When reviewing cusomter accounts, the Container on site Count remains at Zero. See Picture displayed | Issue
62 | Schedule Management screen - Is this configurable - Customer name vs Site Name | assigned | Pramod | 3-normal | 22-Jul-2020 05:56 | ELEMOS WPF | As per screen shot, the schedule management screen shows customers by Cusomter Name, not Site name. So in the example, when there are 3 jobs for the same customer, this is not easily recognisable, as all the customer names are the same. Is this configurable, to display Site Name. The site name can be viewed by hoovering the mouse over the job, but operationally would work better if it was by Site Name. | Enhancement
63 | Call Log Notes not Saving | closed | Jackie | 2-high | 15-Jul-2020 03:47 | ELEMOS Web | When creating a Call Log, you select a category for the communication, but after you write your notes, there is no 'SAVE' option. I try pressing 'Enter' and the lines just keep dropping. | Training
64 | Cannot locate Closed or Pending Closed Customers - Web UI | assigned | Pramod | 2-high | 22-Jul-2020 05:57 | ELEMOS Web | In the WPF version when you search for a customer, there is a 'SHOW INACTIVE' tickbox that can be selected. This allows you to search for customers who are currently suspended, pending close or have been closed. This function does not exist in Web UI, therefore if you need to reactivate a suspended customer, you are unable to find them. | Defect
65 | Dates are in incorrect format | closed | Pramod | 3-normal | 07-Jul-2020 04:48 | ELEMOS Web | Dates for fields requiring a date, are in MM/DD/YY format instead of DD/MM/YY | Issue
66 | Call Log Reasons Uneditable | assigned | Jackie | 2-high | 14-Jul-2020 03:11 | ELEMOS Web | There is no field to adjust the pre-set reason codes for the Call Logs in Web UI. | Enhancement
67 | Liquid Service - Requires Materials | closed | Karen | 2-high | 07-Jul-2020 06:37 | ELEMOS WPF | Attempting to create a liquid service using ELEMOS WPF or WEB is not possible. Material is a mandatory field and, unfortunately, none have been configured for Service Type of LIQUID. | Issue
68 | Transactional Detail report does not balance to GL Customer Browser Inv work | ready to test | Carlo | 2-high | 15-Jul-2020 01:05 | ELEMOS WPF | ACC1009 Expected Value column F =78,340.15 ex gst (with GST $86174.16) This should match what is displayed as invoiceable work instead we have a total $85,624.16) Invoicable work was missing job JB1000 JPS2088 Parameters used: Select all | Issue
69 | Generate preview invoice on customer screen is not working | closed | Alex | 2-high | 09-Jul-2020 04:35 | ELEMOS WPF | Was expecting invoice PDF to appear with transactional data Got a blank error page Modified advanced settings and invoce appeared | Issue
70 | Financial Confirmation- Add a Supplier cost to a completed job | assigned | Alex | 2-high | 15-Jul-2020 01:33 | ELEMOS WPF | Expected to be able to select supplier & cost agreement against job Grill'd Parramatta Got an error message | Issue
71 | Toggle View feature not working | assigned | Pramod | 2-high | 22-Jul-2020 12:13 | AMCS Mobile | This was a persistant issue raised in 2020.1, and was to be rectified in 2020.2. When you go to Toggle View and turn off the maps, the runsheet shows on a full screen. Then if you go back and turn the maps back on. The maps return. If you repeat this process, the full screen of a runsheet is not avialble anymore. | Issue
72 | On Call jobs not able to be sent to Devices | closed | Carlo | 1-showstopper | 21-Jul-2020 06:10 | ELEMOS WPF | During Proskips Simulation, we had a major issue with dispatching jobs during the day to the devices. On Call job was created, and then allocated to a vehicle. The "Send Job to All Runs" was done, but the jobs would appear with an orange dot, identifying an issue with the job. The jobs never came across to the device, imapcting the simulaiton on 2 jobs at the end of the day. | Issue
73 | Ability to add extra photos in Unified workflow | assigned | Pramod | 2-high | 22-Jul-2020 12:13 | AMCS Mobile | During the Proskips simulation, if photos had been taken form the front screen of the job, and if we went onto customer signature but wanted to then take additional images, the "Take Photo" button was not available. | Issue
74 | Container Bin number capture not available for Exchange jobs - Unified Workflow | assigned | Pramod | 2-high | 22-Jul-2020 12:13 | AMCS Mobile | During the ProSkips simulation, we identifed that when a container (job) is an Exchange (removing a full bin and dropping an empty container), there is no functionality to record the Full contianer number/tag as well as the empty container. This process works well for Removal & Delivery jobs, but for Exchanges there is no functionality to track Container numbers (ID's). | Issue
75 | Container Delivery - Job doesn't complete | assigned | Pramod | 2-high | 22-Jul-2020 12:13 | ELEMOS WPF | To recreate: 1. Create a container delivery job and pushed to a delivery route featuring a Crane Truck 2. The Job is completed on the OBC, with the user inputting the job details and a signature. 3. Check the job Activity using ELEMOS WPF/WEB Expected: "Bins on Site" on the Open Order should increase by 1 Details input on the OBC should be present Job should be marked as complete Actual Details input on the OBC are present Bin count on the ORDER does not increase by 1 Job remains as Assigned | Issue
76 | Pickup can be created when there are no bins on site | closed | Pramod | 3-normal | 15-Jul-2020 02:14 | ELEMOS WPF | To recreate using WPF: 1. Bring up the Customer Chocolates of the world 2. View the Order against COHOCOLATE DEL MONDO BANKSTOWN, and note that there are 0 bins on site 3. Create a job for a pickup of 2 bins. Expected: Since there are no bins on site, this shouldn't be possible Actual: Job is created. | Issue
77 | Last Invoice Date - Uneditable | closed | Carlo | 3-normal | 15-Jul-2020 03:49 | ELEMOS Web | If you enter a date in the 'Last Invoice Date' field, you cannot remove it, only change the date. | Training
78 | Service Frequency Sort Inconsistent | closed | Jackie | 4-low | 15-Jul-2020 03:50 | ELEMOS Web | When creating a new order, the 'Service Frequencyl' field has our preset frequencies, but they are not in a flowing format. They should be like the below example: 1. On-Call 2. Weekly 2. Fortnightly 3. Three Weekly | Issue
79 | Material Cannot be selected on Order | closed | Pramod | 1-showstopper | 08-Jul-2020 05:01 | ELEMOS Web | Despite being able to set the waste type on the Service Agreement, you are required to select the material on the order but the drop-down selection has no options available. this prevents us from being able to make orders, as this is a mandatory field | Issue
80 | Service Frequency cannot be edited | assigned | Pramod | 2-high | 15-Jul-2020 02:44 | ELEMOS Web | You cannot edit the collection/service frequency on an order. The only option to make a change is to order an action (delivery, empty etc.) | Issue
81 | Cannot Suspend or Cancel active account | closed | Carlo | 2-high | 10-Jul-2020 00:56 | ELEMOS Web | There is no option to place a customer on suspend, pending close or cancelled. | Issue
82 | No option to add Customer Name or Standing PO to ADHOC service | assigned | Pramod | 3-normal | 15-Jul-2020 02:48 | ELEMOS Web | When you are adding an on-call pick-up to a routed service, there is no field to enter the name of the customer contact requesting the collection. In WEB, there is also no lookup that links a standing P/O number to this service. However, in WPF, a lookup exists. | Defect
83 | System 404 Error when attempting to open an Active Order | assigned | Pramod | 2-high | 16-Jul-2020 01:13 | ELEMOS Web | When there are more than 5 Active Contracts and you try and click to open one of them from the expanded screen option, you receive a 404 error notification. - Unable to add Form 44 to additional Service | Issue
84 | Search Bar in WEB doesn't take user to the exact record | closed | Pramod | 3-normal | 16-Jul-2020 00:47 | ELEMOS Web | to recreate in WEBUI: 1. Input 1042 in the search bar at the top of ELEMOS WEB 2. Click on the Service Location "CONDEV TSS HIGH SCOOL" Expected: WEBUI should take the user to the service location Editor for the record "CONDEV TSS HIGH SCOOL" Actual: WEBUI takes the user to the customer CONDEV Constructions ACC1014 | Issue
85 | Variation 117 - Searchable using WPF | assigned | Pramod | 2-high | 13-Jul-2020 06:08 | ELEMOS WPF | Whilst it is understood that CSOs should be using WEB (where this functionality works), there are other teams that will use WPF. It is envisaged that users from those teams will also want to search by site number. To recreate in WPF: 1. Attempt to search using Address, Site Area, Site Name or Customer Name of 1042 Expected: User should be able to search using site number. Actual: There is no selectable value that allows this functionality. | Issue
86 | Filtering On Call (Un-allocated) jobs on Material | assigned | Pramod | 2-high | 21-Jul-2020 23:48 | ELEMOS WPF | In the Route Planning sector when you have a job with a Maerial profile of General Waste - General Waste, the system lets you put this job onto any route, even if that route has a destination eg. Visy Recycling that can only take Recyclable - Paper & Cardboard. The thinking would be that for disposal sites whihc can take all types of waste, you'd establish these sites with each of the mateirals, and for sites that can only take specific materials, eg. Paper & Carboard, this would be set. Then when allocating, the system would verify that the Materials proposed to be put on that run are acceptable by that Destination disposal point. | Enhancement
87 | Error appears during Route Creation | assigned | Pramod | 3-normal | 14-Jul-2020 00:27 | ELEMOS WPF | The attached picture shows the error that appeared on the screen when generating 2 routes today. The Routes did create, but interested to know what this error is and why. | Issue
88 | Form 44 not passing to AMCS Mobile | closed | Chris | 2-high | 13-Jul-2020 04:03 | ELEMOS WPF | We have recently added a number of Form 44 documetns to customers. The Form 44 has been added after the account was set up. When sent to the Mobile, only Comfortdegro's F44 came ot the mobile device, the rest did not come across. Is there a setting or process that needs to be followed to make htis work. Run 303 Friday at Wetherill Park is the Run, and many of these listed belwo are on this run. Customers set up with F44's. Advance Stainless Steel Comfortdelgro Concrete Structures Cork & Chroma Crossover I.T. Franks Mechanical Repairs Drivas Property Group Goodman/Foundation Park Grill'd Crows Nest Grill'd Darlinghurst Grill'd Parramatta Healthmax Innovative Joinery Andiamo Trattoria Nikpol Ronis Real Estate Creativity Inc Pasha's Turkish Restaurant | Issue
89 | Inability to capture Disposal Docket image in Routed work | assigned | Pramod | 3-normal | 22-Jul-2020 12:11 | AMCS Mobile | In scheduled work as part of unified workflow, disposal dockets can now be captured. This is not avaialble in Routed Work? It is part of the paperless truck, to enable drivers to capture images of Disposal Dockets. We thought this was part of 8.3 enhancements | Issue
90 | Route Confirmation : Disposal weights incorrect - Impacted by UOM and Conversion Factor | ready to test | Carlo | 2-high | 16-Jul-2020 01:13 | ELEMOS WPF | When confirming a route, the weight of disposal is being adjusted with the conversion factor. As a result, 5120kg, is presenting as 5,120,000kg. See Attachements. Can we please review and sort out our units of measure, urgently. | Issue
91 | Variation 278 - Form 44 is created, but error message still appears when assigning job to route | ready to test | Carlo | 2-high | 13-Jul-2020 06:22 | ELEMOS WPF | To recreate: 1. Using the Health and Safety tab, add a Form 44 in ELEMOS WEB 2. In Elemos WEB, Create a Callout Job against the site 3. Allocate the job to a route using ELEMOS WPF Expected: Since a valuid Form 44 exists, no warning should appear Actual: A warning appears. | Issue
92 | Variation 278 - Form 44 does not have a timestamp | closed | Pramod | 3-normal | 13-Jul-2020 06:24 | ELEMOS Web | To recreate: 1. Locate customer in WEB 2. Click on the Site 3. Click on Health and Safety 4. Upload a Form 44. Expected: According to the Change description in thee requirements document: * When an initial Site Inspection has been carried out and the Form 44 has been completed, it must be possible to store this information at Customer Site level. * This form must be able to be updated with a relevant timestamp Actual: The web form only has Date Created. No space for a timestamp. | Issue
93 | End date of Form 44 - Optional and not Mandatory | assigned | Pramod | 2-high | 14-Jul-2020 03:06 | ELEMOS Web | If you do not have an end date for the validity of a Form 44, the document does not push down to the OBC. This is currently an optional field, but if we need this to send it down, we need to make this mandatory | Enhancement
94 | Not possible to type in date. | assigned | Pramod | 3-normal | 16-Jul-2020 01:51 | ELEMOS Web | When keying a date in, users are unable to manually type the dates in, but must work backwards to select the year, then the month and then the date - All Click Based | Issue
95 | AMCS Mobile crashes when trying to access Form 44 | closed | Pramod | 1-showstopper | 21-Jul-2020 06:11 | AMCS Mobile | When in AMCS mobile, clicking on the Orange diamond causes the device to crash the app. See video attached. | Issue
96 | Cannot place future exclusion on Orders | assigned | Pramod | 2-high | 16-Jul-2020 02:16 | ELEMOS Web | If we need to place a future-dated suspension of an order (Holiday closure, renovations etc.) there is no ability to do this. | Issue
97 | Cannot Update Future-Dated pricing on orders | fixed | Jackie | 2-high | 16-Jul-2020 04:09 | ELEMOS Web | Even with a current active price having an end date, you cannot add a future-dated price to come into effect once the current one has expired | Defect
98 | AMCS Mobile regularly logged out, requiring reset during ProSkips simulation | assigned | Pramod | 1-showstopper | 17-Jul-2020 07:55 | AMCS Mobile | During the ProSkips simulation, the device would log out, or restart every 30 mins or so. Requiring the user to re-enter user name and password to access Elemos. | Issue
99 | Cannot Set Access Times on Order Level | assigned | Pramod | 2-high | 14-Jul-2020 00:59 | ELEMOS Web | In WPF you can set access on each specific order which caters to customer requirements, however in Web UI, you can only set hours on a site level. | Issue
100 | Lost ability to Check or confirm number of pick ups | assigned | Pramod | 2-high | 14-Jul-2020 07:18 | AMCS Mobile | Something has changed again. Last week, when we went to service a customer, by click,ing on the Green tick a window came up, which asked how many contianers have been services, It defaulted to the number of services on the order, but had a plus and minus sign to adjust. This function has disappeared. See video attached | Issue
101 | Proof of Service - Address the configurations. Every job requires a signature | closed | Pramod | 2-high | 22-Jul-2020 12:08 | ELEMOS WPF | The Proof of Service flag on the cusomter records automatically is turned on. This then requires a signature to be obtained for every pick up. We need this field to be defaulted to off, and then if we require a signature, then it is turn on. There are a number of locations at the Cusomter level & service agreement level where a flag is avialable for a Proof of Service. Can AMCS please provide SUEZ with advice as to what eahc of these should be set to, and what funcitonality the Proof of Serivce does at the Service agreement level. Where is this set in the Web UI version? How do we get these fileds set to defaults. See attached video. | Training
102 | ELEMOS Sub-Contractor Portal. Missing Weight | assigned | Conrad | 2-high | 16-Jul-2020 01:23 | ELEMOS WPF | Once sub-contractor transaction is comleted in Portal and sent back to ELEMOS - the entered weight (by sub-contractor) is missing in ELEMOS | Defect
103 | ELEMOS Sub-Contractor Portal. Missing Volume | assigned | Conrad | 2-high | 16-Jul-2020 01:23 | ELEMOS WPF | The serviced jobs volumes are missing when transacations are sent from the PORTAL to ELEMOS. | Defect
104 | Sub-Contractor Portal Transactions: Charges are missing in ELEMOS | assigned | Conrad | 2-high | 16-Jul-2020 01:23 | ELEMOS WPF | Subcontractor Portal transactions failed to generate any charges in ELEMOS. | Defect
105 | Volume is not passing though to Customer records - After completed a route, the volume is not coming through onto the customers activity records. | assigned | Pramod | 2-high | 22-Jul-2020 12:11 | ELEMOS WPF | When jobs are completed and financial confirmation confirmed, on the cusomters record of activity, the volume colelcted is not passing through | Issue
106 | Variation 116 - Short Codes are not 3-6 characters | new | Pramod | 3-normal | 21-Jul-2020 00:58 | ELEMOS WPF | 1. Open Business Sector 2. Attempt to put a short code of ABC123 Expected:These short codes should be Alphanumeric 3-6 Characters. This means that codes less than 3 characters should not be possible. Codes more than 6 characters should not be possible. Actual: Short codes are only 5 characters long Codes less than 3 characters long are accepted. | Issue
107 | Variation 457 - Change Log on Web is missing the latest change | new | Pramod | 2-high | 21-Jul-2020 03:05 | ELEMOS Web | To recreate: 1. Using WPF, change the value of Ordered By to "change 1" 2. Click Save 3. Using WPF, change the value of Ordered By to "change 2" 4. Click Save 5. Locate the record in Web and click on "View Change Log" Expected: Two changes should be listed, listing details corresponding to "Change 1" and "Change 2" Actual: Two changes are listed. The first shows a blank change. The second shows "Change 1". | Issue
108 | Variation 7 - Time Zone selection dropdown in WEB does not show the values ticked | new | Pramod | 2-high | 21-Jul-2020 03:42 | ELEMOS Web | To recreate in WEB 1. Click on Settings on the top right 2. Click on Time Zone Configuration 3. Ensure that no other values apart from Australia/Sydney and Australia/Perth is ticked 4. Bring up the customer Healthmax 5. In the Call logs section, check the values listed in the time zone dropdown Expected: Should display Australia/Sydney and Australia/Perth only Actual: Displays Australia/Brisbane, Australia/Broken Hill and Australia/Sydney | Issue
109 | WPF - Cannot create a new Customer | new | Pramod | 2-high | 21-Jul-2020 08:16 | ELEMOS WPF | To recreate: 1. Using WPF, go to the CUstomer Home Sector 2. Input "Turtles" in the customer search. CLick on the magnifying glass Expected: The behaviour in 8.3.0.42 allowed the user to click the "New Customer" button after a search was conducted. Actual: After performing a search, the New Customer button is still greyed out. | Issue
111 | Form 44 - Not available on WPF | new |  | 2-high | 23-Jul-2020 02:01 | ELEMOS WPF | To recreate: 1. Login to WPF 2. Locate a Customer site 3. Look for the Health and Safety Tab Expected: Health and Safety Tab exists Actual: No such tab exists | Issue